## Sprint1
MRR Report | [6 empty] | Legend
Bagel Bar Mobile: Sprint 1 | [6 empty] | Severity |  | Status (State)
CSC 355-020 Software Engineering II | [6 empty] | Critical Error: | 1 | Open
Professor: Dr. Tan | [6 empty] | Major Error: | 2 | Assigned
Team C | [6 empty] | Minor Error | 3 | Fixed
Spring 2020 | [6 empty] | Enchancement: | 4 | Closed
Failed
Not Relevant (NA)
ID | Status | Found By | Date Found | SEV | Assigned | Category | Brief Summary | Description (How to reproduce)
1 | Assigned | Stephen Magrowski | 2020-02-01 | 4 | Stephen Magrowski | Mobile App | Email input validity | User input for email address does not check for valid input. Should have reg expression to check for '@' at least.
2 | Assigned | Stephen Magrowski | 2020-02-02 | 4 | Stephen Magrowski | Mobile App | Image sizing | Images do not fit well across different devices/screen sizes. Ex) Iphone 8 vs Android Tablet.
3 | Assigned | Stephen Magrowski | 2020-02-03 | 3 | Stephen Magrowski | Mobile App | Input error check | Invalid user input messages do not print to the screen, only to the debugging console.
4 | Assigned | Stephen Magrowski | 2020-02-03 | 4 | Stephen Magrowski | Mobile App | User password input | User password input is not hidden when being entered.
5 | Assigned | Stephen Magrowski | 2020-02-03 | 4 | Stephen Magrowski | Mobile App | User password input | User password input should be 8 or more characters, there is no validation.
6 | Assigned | Stephen Magrowski | 2020-02-04 | 4 | Stephen Magrowski | Mobile App | Invalid login | When the user enters an incorrect email/password combo the error message persists on the screen even after the input fields are changed.